Assignment 1

| CONTEMPORARY MANAGEMENT Assignment 1 |  |  |
| --- | --- | --- |
| Student ID |  | Student Name |  |
| Job title: My role in detail (Job title and brief job description): Brief about company: - . - . - Responsibilities: - Distribute rejection notifications within concerned depts. & collect results of investigations. - To analyze data in order to support decision-making taking the necessary measures based on facts. - Early risk detection. - Share knowledge between partners and stakeholders. - Our crucial task is to reduce the number of rejection notifications against Egyptian shipments of fresh produce especially Oranges due to exceeding the (MRL) of pesticide residues used at pre-harvest stages. |  |  |  |
| Planning |  |  |  |
| Goal | Main Goal: |  |  |
|  | * Short-term Goal: - Reduce number of EU rejection notifications against Egyptian shipments of Oranges due to exceeding the maximum residue levels (MRL) of pesticide residues, by 25% by June 2026. - Increase number of establishments that comply with food safety requirements that produce and exports fresh produce especially to the EU by 40% by June 2026. * Long-Term Goal: Ensure long-term compliance of Egyptian fresh produce with EU MRLs to prevent increases in official controls, maintain rejection rates below 20% for 3 consecutive years by June 2029 |  |  |
|  | Time frame: 12 months Target: - Reduce number of EU Oranges rejection notifications by 25% - 40% increase in number of complying establishments to food safety requirements. |  |  |
| Strategies | - Data analysis of rejection notifications to identify the common pesticides occur as reason for rejections |  |  |
|  | - Intensifying inspection visits on establishments to urge rapid fulfillment of measures required for compliance with food safety requirements. |  |  |
|  | - Establish a risk-based monitoring plan for oranges shipments to ensure compliance with export requirements. |  |  |
|  | - Conduct monthly meetings with stakeholders; FBOs including processors & Exporters, Agricultural Export Council, Central Administration of Plant Quarantine to enable a structured approach and smooth compliance, ensuring alignment with EU export requirements. |  |  |

| Strategies | Plans |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Steps | Responsible | Timeline | Resources | KPIs | Success Criteria |
| A. Data analysis of rejection notifications to identify the common pesticides occur as reason for rejections | A.1 Pesticide Identification & Frequency Analysis: to identify the most frequently cited pesticide residues causing rejections from compiled data for the past 3 years. Categorize by pesticide, crop specifically Oranges & farms & exporters. | Rapid Alert Unit | 10 days of 1st Month. | - Data analysts, agricultural experts. - Statistical software (Spread Sheet) & database - RASFF Portal Access - Farm codes | - Clean & accurate compiled data. - Reporting on time | - Completion of analysis report within timeframe. - Identification of at least top 5-10 frequently cited pesticides & root causes for each. - Implementation of recommendations. |
|  | A.2 Root Cause Investigation for top identified pesticides, reviewing approved pesticides list, farming practices, regulations | Rapid Alert Unit, Lab. Dept. & CAPQ | 10 days of 1st Month. Depends on completion of A.1 |  |  |  |
|  | A.3 Recommendations & Follow-Up: prepare report of detailed findings, identifying problematic pesticides & provide recommendations for intervention to achieve goals. Follow-up for implementing the recommendations. | Rapid Alert Unit | 10 days of 1st Month. Depends on completion of A.1 |  |  |  |
| B. Intensifying inspection visits on establishments to urge rapid fulfillment of measures required for compliance with food safety requirements. | B.1: Establish Target List: Identify current list of EU-exporting establishments and their last compliance status. Create a target list of establishments requiring intensified visits (with previous non-compliance, new exporters, & those flagged by data analysis from Strategy a). | Packing House Inspection Dept. & Rapid Alert Unit | 2nd month & onwards throughout the year | - Trained inspectors, an administrative for scheduling/tracking - Inspection checklists - Software (Spread Sheet) for tracking compliance status. - Regulations. | - Establishment of Checklist - Number of visits - Number of complying Establishments | - Intensified inspections conducted as planned. - Good response of establishments. |
|  | B.2: Develop Inspection checklist: engagement of Inspectors to develop a checklist focusing on key food safety requirements and common non-compliance issues (e.g., control of pesticides in raw material, HACCP, Traceability). | Packing House Inspection Dept. |  |  |  |  |
|  | B.3 Schedule & Conduct Intensified Visits: Plan and execute the schedule of intensified visits to target establishments. | Packing House Inspection Dept. |  |  |  |  |
|  | B.4: Follow-up & Corrective Action Tracking: Track corrective actions required from establishments, set deadlines, and conduct follow-up audits to verify implementation. | Packing House Inspection Dept. |  |  |  |  |
|  | B.5: Reporting: Regularly report on compliance status changes and provide feedback to establishments & Agricultural Export Council. | Packing House Inspection Dept. |  |  |  |  |
| - Establish a risk-based monitoring plan for oranges shipments to ensure compliance with export requirements. | C.1: Risk Assessment Framework: Develop a framework to assess risk levels for orange shipments based on (frequently cited pesticides, high-risk farms / exporters, type of cultivation practices and previous rejection history. | Lab. Dept., Packing House Inspection Dept., Export Dept., Rapid Alert Unit & CAPQ | Start 3rd month onwards throughout the year | - Lab Researchers - Database of accredited labs with required scope of tests. - Software (Spread Sheet) for traceability - List of Codes of Oranges’ Farms - Regulations | - Establishments of Monitoring Plan - Number of collected samples - Number of conforming samples - Effective traceability system | - Implementation of the monitoring plan within the timeframe. - Reduction in the detection of high-risk pesticides in pre-shipment tests. - Robust system of origin tracing for rejected consignments. |
|  | C.2: Sampling & Testing Plan: Design a risk-based sampling and testing plan for oranges, including frequency of testing, sample size, multi-residue analysis, specific pesticides, and accredited labs. | Lab. Dept., |  |  |  |  |
|  | C.3 Traceability System: Implement "from farm to export" traceability system for oranges, to identify the origin of any non-conforming consignment | Lab. Dept., & CAPQ |  |  |  |  |
|  | C.4: Enforcement & Feedback: Establish clear procedures for handling non-conforming; detention, re-routing or destruction & provide feedback to farmers/exporters /inspectors to take required measures. | Packing House Inspection Dept., Export Dept., |  |  |  |  |
|  | C.5: Regular Review & Adjustment: review the effectiveness of the monitoring plan periodically & adjust sampling frequencies or parameters based on new data or changing risk levels. | Lab. Dept., |  |  |  |  |
| - Conduct monthly meetings with stakeholders; FBOs including processors & Exporters, Agricultural Export Council, Central Administration of Plant Quarantine to enable a structured approach and smooth compliance, ensuring alignment with EU export requirements | D.1: Define Meeting Objectives & Agenda: Clearly define the purpose of these monthly meetings (e.g., review progress on compliance, discuss challenges, share EU updates, coordinate interventions, present analysis findings). | Rapid Alert Unit, Lab. Dept., Packing House Inspection Dept. | Start 2nd Month & onwards | - Meeting facilitator, minute-taker - Meeting venue /virtual meeting platforms - email, shared folder - Regulations | - Stakeholders Attendance - Key info dissemination - Developed Action Plans | - Improved understanding & alignment among stakeholders regarding EU requirements & compliance efforts. - Completion rate of action items generated from meetings. - Enhancing cross-organizational communication collaboration & problem-solving |
|  | D.2: Establish Communication Channels: Set up formal communication channels; email group, shared folder for sharing meeting agenda, materials, minutes, & updates. | Rapid Alert Unit, IT Dept. |  |  |  |  |
|  | D.3: Schedule & Facilitate Meetings: Secure a monthly platform & venue (physical or virtual). Assign a facilitator to manage meetings, ensure adherence to agenda. | Rapid Alert Unit, |  |  |  |  |
|  | D.4: Disseminate Information & Follow-up: Distribute meeting minutes, action items, and relevant updates promptly after each meeting. Assign clear responsibilities & deadlines for troubleshoot emerging issues, develop joint action plans, and follow up on their completion. | Rapid Alert Unit, |  |  |  |  |

| Organizing |  |  |
| --- | --- | --- |
| What to be done? who will do it and how? | All Teams have to: - Exchange information within all participating Depts. on time, - Delegate tasks and cross-functional collaboration, - Holding bi-weekly project follow-up meetings with heads of all participating Depts. to track progress, resolve obstacles and eliminate costs that hinder the workflow. Team: - Rapid Alert Unit Team: Compiling & enhance required data in the identified spread sheets & adhered to the importance of their role & consequences, communicate with CAPQ & AEC, adhering to time frames, final reporting, oversee all achievements & follow up with reports of KPIs from all teams. - Packing House Inspection Dept. Team: Plan efficiently for visits, be aware of priorities, perform subjectively & effective reporting. - Labs Dept. Team: Consolidate the monitoring plan, re-adjust due to updates, follow-up with implementation & results recording on the identified spread sheets. - Export Dept. Team: Provide data about exporters & any measures taken against non-compliance. - Quality dept.: Assure using controlled documents & setting valid KPIs. - Finance Dept. Team: Provision of budget for allocating resources, ex. Sampling tools & utensils, securing avenues for monthly meetings. - Vehicles Dept. Team: Quick response in provision of vehicles for inspectors to conduct unannounced visits. - IT Dept. Team: Technical support during virtual meetings & technical software. - Executive Manager: Mitigate risks & resolve obstacles. |  |
| Reporting lines | - Rapid Alert unit report achievements & challenges to NFSA Executive Manger & communicate report with recommendations to participating Teams & partners. - Labs Dept., Export Dept. & Packing house Inspection Dept. reports to Rapid Alert Unit. - Executive Manager reports to Top Management. - Approved Final Report to be disseminated to Top Management, Executive Manager, all participating depts. & partners by Rapid Alert Unit. |  |
| Centralization VS. Decentralization in decision making | Centralized: Rapid Alert unit for compiling required data & reporting progress, achievements & final reporting, Packing House Inspection Dept. for establishing focused inspection checklist, Lab. Dept. for establishing the monitoring plan & interpretation of tests results, Finance for budget provision. Decentralized: Packing House Inspection Dept. for conducting diversified inspection visits, Export Dept. for physical check of exported shipments, Vehicles Dept. for distributing vehicles. |  |